## Project Charter
E-COMMERCE WEBSITE TESTING — PROJECT CHARTER
Project Name | E-Commerce Website Testing Project
Project Purpose | Validate the complete e-commerce flow (browse, cart, checkout, payment, order management) for functional correctness, performance, security, cross-browser compatibility, and responsiveness prior to release.
Objectives | 1) Verify all functional workflows across the buying journey. 2) Validate integration between modules (catalog, cart, payment, inventory, shipping, notifications). 3) Confirm end-to-end (E2E) flows work as a real user would experience them. 4) Assess performance under expected and peak load. 5) Identify security vulnerabilities (OWASP Top 10 focus). 6) Confirm consistent behavior across browsers, devices, and screen sizes. 7) Build a maintainable automation suite for regression. 8) Track and manage all defects through JIRA to closure.
In Scope | Product browsing/search, product detail pages, cart, wishlist, checkout, payment gateway integration, user account/registration/login, order history, order tracking, email/SMS notifications, admin/catalog management (if applicable), returns/refunds flow.
Out of Scope | Internal payment gateway provider's own infrastructure (only integration points are tested), third-party logistics backend systems, marketing/CRM tools not directly tied to the storefront.
Key Stakeholders | Product Owner, QA Lead, Dev Lead, DevOps/Release Manager, Business/UAT Sign-off Owner
Project Sponsor | [Name / Role]
QA Lead | [Name]
Start Date | [Start Date]
Target Completion Date | [End Date]
Success Criteria | All critical/high priority test cases executed with 95%+ pass rate; zero open critical/blocker defects at release; performance benchmarks met (see Test Plan); security scan shows no high-risk open findings; automation suite covers all P1 regression flows.

## Test Scope
TEST SCOPE — FEATURES, TYPES, PLATFORMS, LEVELS
Category | Details | Priority | In/Out
Features to Test | Product search & filtering | High | In
Features to Test | Product detail page (images, price, variants, reviews) | High | In
Features to Test | Shopping cart (add/update/remove, quantity, coupons) | Critical | In
Features to Test | Wishlist / Save for later | Medium | In
Features to Test | Checkout flow (address, shipping, payment, order review) | Critical | In
Features to Test | Payment gateway integration (cards, wallets, COD) | Critical | In
Features to Test | User registration, login, password reset | Critical | In
Features to Test | Order history & order tracking | High | In
Features to Test | Email/SMS notifications (order, shipping, promo) | Medium | In
Features to Test | Returns & refunds workflow | High | In
Features to Test | Admin catalog/inventory management | Medium | In
Features to Test | Payment provider's internal infrastructure | - | Out
Types of Testing | Functional testing | Critical | In
Types of Testing | Integration testing | Critical | In
Types of Testing | End-to-End (E2E) testing | Critical | In
Types of Testing | Performance testing (load, stress, spike, soak) | High | In
Types of Testing | Security testing (OWASP Top 10, auth, payment data) | Critical | In
Types of Testing | Cross-browser testing (Chrome, Firefox, Safari, Edge) | High | In
Types of Testing | Responsive / mobile-web testing | High | In
Types of Testing | Regression testing | High | In
Types of Testing | Usability/accessibility testing (WCAG basics) | Medium | In
Platforms | Web — desktop (Chrome, Firefox, Safari, Edge latest 2 versions) | High | In
Platforms | Web — responsive breakpoints (mobile/tablet widths) | High | In
Platforms | Mobile web (iOS Safari, Android Chrome) | Medium | In
Platforms | Native mobile apps (iOS/Android) | - | Out (Phase 2)
Platforms | API layer (REST endpoints for catalog, cart, order, payment) | Critical | In
Test Levels | Unit testing (developer-owned, verified via coverage report) | - | Dev-owned
Test Levels | Integration testing (module-to-module, service-to-service) | Critical | In
Test Levels | System testing (full application, E2E flows) | Critical | In
Test Levels | Acceptance testing (business/UAT sign-off) | High | In
Automation vs Manual | Smoke suite (post-deploy) — Automated | Critical | In
Automation vs Manual | Regression suite (checkout, cart, login, search) — Automated | Critical | In
Automation vs Manual | API test suite — Automated (Postman/Newman) | High | In
Automation vs Manual | Exploratory & usability testing — Manual | Medium | In
Automation vs Manual | New/unstable feature testing — Manual first, automate once stable | Medium | In
Automation vs Manual | Visual/UI edge cases — Manual | Low | In

## Test Strategy
TEST STRATEGY
Testing Approach | Risk-based and requirement-based testing, executed within Agile sprints. Each sprint includes functional test design/execution for new features, automated regression runs, and API testing in CI. Performance and security testing run each release cycle before go-live.
Entry Criteria | Build deployed to QA environment; smoke suite passes; test cases reviewed & approved; required test data available; environment configuration verified.
Exit Criteria | 100% of Critical/High test cases executed; 95%+ pass rate; zero open Critical/Blocker defects; all High defects triaged with agreed resolution/waiver; performance thresholds met; security scan shows no unresolved High findings; test summary report signed off.
Test Environments | DEV (developer sandbox) -> QA (integration & functional testing) -> STAGING (production-like, used for performance/security/UAT) -> PROD (post-release smoke only).
Tools & Techniques
Category | Tool | Purpose
Test Management / Bug Tracking | JIRA | Test case linkage, defect tracking, sprint boards
Functional / E2E Automation | Selenium WebDriver | Cross-browser automated UI regression
Functional / E2E Automation | Playwright (optional) | Fast, reliable E2E automation with built-in waits
API Testing | Postman / Newman | API test collections, CI-integrated API regression
Performance Testing | JMeter | Load, stress, spike, and soak testing
Security Testing | OWASP ZAP | Automated vulnerability scanning
CI/CD | Jenkins / GitHub Actions | Automated test execution on each build
Version Control | Git / GitHub | Automation scripts, test framework source control
Cross-Browser Grid | BrowserStack / Sauce Labs | Cross-browser & device coverage
Roles & Responsibilities
Role | Responsibility | Owner
QA Lead | Strategy, planning, reporting, stakeholder communication | [Name]
Test Engineers | Test case design, manual execution, defect logging | [Name(s)]
Automation Engineers | Framework build, script development/maintenance | [Name(s)]
Performance Engineer | Load/stress/spike test design & execution | [Name]
Security Tester | Vulnerability scanning, penetration test coordination | [Name]
Dev Team | Unit testing, defect fixes, code reviews | [Team]
Product Owner / BA | Requirement clarification, UAT sign-off | [Name]

## Test Plan
TEST PLAN
Objectives | Validate that the e-commerce platform's core buying journey is functionally correct, performant under load, secure against common vulnerabilities, and consistent across browsers and screen sizes before release.
Scope — In | Catalog/search, product detail, cart, checkout, payment integration, account management, order tracking, notifications, returns/refunds, automation suite, cross-browser & responsive checks.
Scope — Out | Payment provider's internal systems, third-party logistics backend, native mobile apps (Phase 2), marketing/CRM tools not tied to the storefront.
Schedule | Week 1: Test planning & strategy finalization. Week 2: Test case design (functional, API, E2E). Week 3-4: Environment/tooling setup + automation framework build. Week 5-6: Test execution cycle 1 (functional, integration, E2E). Week 7: Performance & security testing. Week 8: Cross-browser/responsive testing + regression cycle 2. Week 9: Defect fixes verification, UAT support. Week 10: Exit report, sign-off, release readiness review.
Resources | 1 QA Lead, 2-3 Test Engineers, 1-2 Automation Engineers, 1 Performance Engineer, 1 Security Tester (or external vendor), QA/Staging environments, JIRA + Selenium + Postman + JMeter licenses/access.
Test Deliverables | Test strategy document, test cases (functional/API/E2E), automation scripts & framework, performance test report, security scan report, defect reports, traceability matrix, test summary/exit report.
Approval Process | Test plan reviewed by QA Lead and Dev Lead -> approved by Product Owner -> exit report reviewed at go/no-go meeting -> final sign-off by Product Owner and QA Lead.

## Risk Assessment
RISK ASSESSMENT
Risk | Likelihood | Impact | Severity | Mitigation | Owner
Payment gateway sandbox instability delays checkout testing | Medium | High | High | Set up mock/stub payment responses in parallel; coordinate early with provider for sandbox access | QA Lead
Requirements change mid-sprint affecting test cases | High | Medium | High | Maintain traceability matrix; review requirement changes in sprint planning before test design | QA Lead / BA
Test environment downtime or data reset issues | Medium | High | High | Automate environment/data provisioning; schedule environment health checks before each cycle | DevOps
Performance testing reveals late-stage bottlenecks | Medium | High | High | Run performance tests early (not just before release) on critical flows (checkout, search) | Performance Engineer
Security vulnerabilities found close to release | Low | Critical | High | Run automated security scans continuously in CI, not only at the end of the cycle | Security Tester
Automation script flakiness causing false failures | Medium | Medium | Medium | Use explicit waits, stable locators, and a Page Object Model; review flaky tests weekly | Automation Engineer
Cross-browser inconsistencies discovered late | Medium | Medium | Medium | Integrate cross-browser runs into CI from the start using BrowserStack/Sauce Labs | Test Engineers
Third-party integration (shipping/tax API) downtime | Low | High | Medium | Use service virtualization/mocks for dependent third-party APIs during test execution | Automation Engineer
Resource availability (team members pulled to other projects) | Medium | Medium | Medium | Cross-train team members on multiple modules; maintain buffer time in schedule | QA Lead
Tight release timeline compresses test execution window | High | High | Critical | Prioritize test cases by risk; parallelize manual and automated execution; negotiate scope if needed | QA Lead / PM

## Task Breakdown
TASK BREAKDOWN & MILESTONES
Task | Owner/Team | Start Week | End Week | Status | Deliverable / Milestone
Finalize test strategy & test plan | QA Lead | Week 1 | Week 1 | Not Started | Test Strategy Document
Design functional test cases (catalog, cart, checkout, account) | Test Engineers | Week 2 | Week 2 | Not Started | Test Case Repository
Design API test cases | Automation Engineers | Week 2 | Week 2 | Not Started | API Test Suite (Postman)
Design E2E test scenarios | Test Engineers | Week 2 | Week 3 | Not Started | E2E Scenario Docs
Set up JIRA project & workflows | QA Lead | Week 1 | Week 1 | Not Started | JIRA Board Configured
Set up test environments (QA/Staging) | DevOps | Week 3 | Week 3 | Not Started | Environment Ready
Prepare test data sets | Test Engineers | Week 3 | Week 3 | Not Started | Test Data Sets
Set up GitHub repo & branching strategy | Automation Engineers | Week 3 | Week 3 | Not Started | GitHub Repository
Build Selenium automation framework (POM) | Automation Engineers | Week 3 | Week 4 | Not Started | Automation Framework
Automate smoke & regression suite | Automation Engineers | Week 4 | Week 6 | Not Started | Automated Regression Suite
Execute functional/integration testing — Cycle 1 | Test Engineers | Week 5 | Week 6 | Not Started | Execution Report Cycle 1
Execute E2E testing | Test Engineers | Week 6 | Week 6 | Not Started | E2E Execution Report
Set up & execute JMeter performance tests | Performance Engineer | Week 7 | Week 7 | Not Started | Performance Test Report
Conduct security scan (OWASP ZAP) | Security Tester | Week 7 | Week 7 | Not Started | Security Test Report
Cross-browser & responsive testing | Test Engineers | Week 8 | Week 8 | Not Started | Cross-Browser Report
Regression cycle 2 (post-fix verification) | Test Engineers | Week 8 | Week 8 | Not Started | Execution Report Cycle 2
Defect triage & retest | QA Lead / Dev Team | Week 9 | Week 9 | Not Started | Defect Status Report
UAT support | QA Lead / BA | Week 9 | Week 9 | Not Started | UAT Sign-off
Prepare test summary / exit report | QA Lead | Week 10 | Week 10 | Not Started | Test Summary Report
Go/No-Go release readiness review | QA Lead / PM / PO | Week 10 | Week 10 | Not Started | Sign-off Document

## Deliverables
PROJECT DELIVERABLES
Deliverable | Description | Owner
Project Charter | High-level document defining purpose, objectives, stakeholders, and scope | QA Lead
Test Strategy Document | Overall approach, tools, roles, entry/exit criteria, risk handling | QA Lead
Test Plan | Detailed scope, schedule, resources, deliverables, and approval process | QA Lead
Risk Assessment | Documented risks with likelihood, impact, and mitigation plans | QA Lead
Environment Setup | Configured QA/Staging environments with test data and tools ready | DevOps
Task Assignments | Ownership matrix — who does what, by when (see Task Breakdown sheet) | QA Lead
GitHub Repository | Central repo for automation code, test scripts, and CI configuration | Automation Engineers
README / Project Overview | Onboarding doc — summary, setup instructions, how to run tests, folder structure | Automation Engineers
Automated Test Suite | Selenium/Playwright regression suite + Postman API collection | Automation Engineers
Performance Test Report | JMeter load/stress/spike results against defined thresholds | Performance Engineer
Security Test Report | OWASP ZAP scan results and remediation status | Security Tester
Defect Reports (JIRA) | All logged bugs with severity, status, and resolution history | Test Engineers
Test Summary / Exit Report | Final coverage, pass/fail metrics, open risks, release recommendation | QA Lead

## Defect Log Template
DEFECT / BUG TRACKING TEMPLATE (JIRA-STYLE)
Bug ID | Summary | Module | Severity | Priority | Status | Steps to Reproduce | Reported By | Assigned To
BUG-001 | Checkout fails with expired coupon code — no error message shown | Checkout | High | P1 | Open | 1) Add item to cart 2) Apply expired coupon 3) Proceed to checkout | [QA Name] | [Dev Name]
Legend:
This is a template — one example row shown. Add real defects below following the same columns; sync with the live JIRA board.