## Project Charter
SOCIAL MEDIA PLATFORM TESTING — PROJECT CHARTER
Project Name | Social Media Platform Testing Project
Project Purpose | Validate the core social platform experience — account/profile management, content creation and interaction, real-time features, mobile apps, platform performance under load, and content moderation — for functional correctness, scalability, and safety prior to release.
Objectives | 1) Verify registration, login, and profile management flows across web and mobile. 2) Validate post creation, editing, and interaction features (likes, comments, shares, reactions). 3) Confirm real-time features (feed updates, chat, notifications, live status) work reliably. 4) Test native mobile apps (iOS/Android) for functional parity and device compatibility. 5) Assess platform performance and stability under expected and peak concurrent load. 6) Validate content moderation systems (automated filters, reporting, manual review workflows). 7) Track and manage all defects through JIRA to closure.
In Scope | User registration/login/SSO, profile creation & editing, privacy settings, post creation (text/image/video), likes/comments/shares/reactions, feed algorithm display, direct messaging, push/in-app notifications, real-time presence indicators, mobile apps (iOS/Android), content moderation (auto-flagging, user reporting, moderator review queue), performance/load testing.
Out of Scope | Underlying ML/recommendation model training and tuning (only output behavior is tested), third-party ad-network infrastructure, payment/monetization systems (covered separately if applicable), internal moderator tooling admin backend beyond core review workflow.
Key Stakeholders | Product Owner, QA Lead, Mobile Dev Lead, Backend Dev Lead, Trust & Safety Lead, DevOps/Release Manager
Project Sponsor | [Name / Role]
QA Lead | [Name]
Start Date | [Start Date]
Target Completion Date | [End Date]
Success Criteria | All critical/high priority test cases executed with 95%+ pass rate; zero open critical/blocker defects at release; platform sustains target concurrent users with acceptable latency; real-time features (feed, chat, notifications) update within defined SLA; content moderation correctly flags/blocks policy-violating content in test scenarios; mobile apps pass device matrix testing.

## Test Scope
TEST SCOPE — FEATURES, TYPES, PLATFORMS, LEVELS
Category | Details | Priority | In/Out
User Registration & Profiles | Sign-up (email, phone, SSO — Google/Apple/Facebook) | Critical | In
User Registration & Profiles | Email/phone verification & OTP flows | Critical | In
User Registration & Profiles | Login, logout, session/token expiry | Critical | In
User Registration & Profiles | Password reset & account recovery | High | In
User Registration & Profiles | Profile creation/editing (bio, photo, cover image) | High | In
User Registration & Profiles | Privacy settings (public/private account, blocking, muting) | High | In
User Registration & Profiles | Follow/unfollow, friend request workflows | High | In
Post Creation & Interactions | Text, image, video, and multi-media post creation | Critical | In
Post Creation & Interactions | Edit/delete post, draft saving | Medium | In
Post Creation & Interactions | Likes, comments, replies, reactions | Critical | In
Post Creation & Interactions | Share/repost, save/bookmark | High | In
Post Creation & Interactions | Hashtags, mentions (@tagging), link previews | Medium | In
Post Creation & Interactions | Feed generation & ranking display (functional behavior only) | High | In
Real-Time Features | Real-time feed updates (new posts appearing live) | Critical | In
Real-Time Features | Direct messaging / chat (send, receive, read receipts, typing indicators) | Critical | In
Real-Time Features | Push notifications & in-app notifications | Critical | In
Real-Time Features | Online/presence status, live view counts | Medium | In
Real-Time Features | Live streaming / stories (if applicable) | High | In
Mobile App Testing | iOS app — functional parity with web | Critical | In
Mobile App Testing | Android app — functional parity with web | Critical | In
Mobile App Testing | Device/OS version compatibility matrix | High | In
Mobile App Testing | App permissions (camera, mic, location, contacts, notifications) | High | In
Mobile App Testing | Offline behavior & sync on reconnect | Medium | In
Mobile App Testing | App store build/release smoke testing | High | In
Performance Under Load | Concurrent user load testing (feed load, post submission) | Critical | In
Performance Under Load | Stress testing (beyond expected peak) | High | In
Performance Under Load | Spike testing (viral content / sudden traffic surge) | High | In
Performance Under Load | Soak/endurance testing (extended uptime) | Medium | In
Performance Under Load | Real-time messaging/notification latency under load | High | In
Content Moderation | Automated content filtering (text, image, video flagging) | Critical | In
Content Moderation | User reporting workflow (report post/comment/user) | Critical | In
Content Moderation | Moderator review queue & actions (remove, warn, ban) | High | In
Content Moderation | Appeal process for moderated content | Medium | In
Content Moderation | Policy-violation edge cases (spam, hate speech, nudity, misinformation) | Critical | In
Types of Testing | Functional, Integration, E2E, Regression testing | Critical | In
Types of Testing | Performance testing (load/stress/spike/soak) | High | In
Types of Testing | Security testing (auth, data privacy, API abuse) | Critical | In
Types of Testing | Cross-browser & responsive testing (web) | High | In
Types of Testing | Mobile testing (iOS/Android native) | Critical | In
Types of Testing | Usability & accessibility testing | Medium | In
Platforms | Web — desktop (Chrome, Firefox, Safari, Edge) | High | In
Platforms | Web — responsive/mobile-web | High | In
Platforms | iOS native app | Critical | In
Platforms | Android native app | Critical | In
Platforms | API layer (REST/GraphQL — feed, post, chat, notification services) | Critical | In
Test Levels | Unit testing (dev-owned) | - | Dev-owned
Test Levels | Integration testing (service-to-service, e.g., post service <-> feed service) | Critical | In
Test Levels | System testing (full E2E user journeys) | Critical | In
Test Levels | Acceptance testing (business/UAT sign-off) | High | In
Automation vs Manual | Smoke suite (post-deploy) — Automated | Critical | In
Automation vs Manual | Regression suite (auth, post, feed, messaging) — Automated | Critical | In
Automation vs Manual | API test suite — Automated (Postman/Newman) | High | In
Automation vs Manual | Real-time feature testing (WebSocket-based) — Automated + Manual | High | In
Automation vs Manual | Mobile automation (Appium) for core flows | High | In
Automation vs Manual | Content moderation edge cases — Manual (exploratory) | Medium | In
Automation vs Manual | Usability/new feature testing — Manual first, automate once stable | Medium | In

## Test Strategy
TEST STRATEGY
Testing Approach | Risk-based and requirement-based testing executed within Agile sprints. Each sprint includes functional/API test design and execution for new features, automated regression, and real-time feature verification (WebSocket/push). Mobile app testing runs against each release candidate build. Performance and content-moderation testing run each release cycle before go-live.
Entry Criteria | Build deployed to QA environment (web + mobile builds available); smoke suite passes; test cases reviewed & approved; test data (seeded users, posts, moderation samples) available; real-time services (chat/notification) reachable in QA environment.
Exit Criteria | 100% of Critical/High test cases executed; 95%+ pass rate; zero open Critical/Blocker defects; performance thresholds met (see Test Plan); real-time feature latency within SLA; content moderation correctly handles all defined policy-violation test scenarios; mobile app matrix testing complete; test summary report signed off.
Test Environments | DEV (developer sandbox) -> QA (functional/integration/real-time testing) -> STAGING (production-like, used for performance/security/UAT, mobile beta builds via TestFlight/Play Internal Testing) -> PROD (post-release smoke only).
Category | Tool | Purpose
Test Management / Bug Tracking | JIRA | Test case linkage, defect tracking, sprint boards
Web Automation | Selenium / Playwright | Cross-browser automated UI regression
Mobile Automation | Appium | iOS/Android native app automation
API Testing | Postman / Newman | REST/GraphQL API test collections, CI-integrated regression
Real-Time / WebSocket Testing | Socket.io test client / custom scripts | Chat, live feed, notification delivery verification
Performance Testing | JMeter / k6 | Load, stress, spike, and soak testing
Security Testing | OWASP ZAP, Burp Suite | Automated vulnerability scanning, API abuse testing
Content Moderation Testing | Custom test data sets + manual review | Verify auto-filtering, reporting, and moderator workflows
CI/CD | Jenkins / GitHub Actions | Automated test execution on each build (web + mobile)
Version Control | Git / GitHub | Automation scripts, test framework source control
Cross-Browser/Device Grid | BrowserStack / Sauce Labs / Firebase Test Lab | Cross-browser & real-device coverage
Roles & Responsibilities
Role | Responsibility | Owner
QA Lead | Strategy, planning, reporting, stakeholder communication | [Name]
Test Engineers | Test case design, manual execution, defect logging | [Name(s)]
Automation Engineers | Web/API framework build, script development/maintenance | [Name(s)]
Mobile QA Engineer | iOS/Android app testing, Appium automation, device matrix coverage | [Name]
Performance Engineer | Load/stress/spike/soak test design & execution | [Name]
Security Tester | Vulnerability scanning, auth/privacy testing | [Name]
Trust & Safety / Moderation QA | Content moderation test design, policy-violation scenario testing | [Name]
Dev Team | Unit testing, defect fixes, code reviews | [Team]
Product Owner / BA | Requirement clarification, UAT sign-off | [Name]

## Test Plan
TEST PLAN
Objectives | Validate that the social media platform's registration/profile, content, real-time, mobile, performance, and moderation systems work correctly, scale under load, and enforce platform policy before release.
Scope — In | Registration/login/profiles, post creation & interactions, real-time feed/chat/notifications, iOS/Android apps, load/stress/spike/soak testing, content moderation (auto-filter, reporting, moderator review), automation suite, JIRA-based defect tracking.
Scope — Out | ML recommendation model tuning, third-party ad infrastructure, monetization/payment systems, internal moderator admin backend beyond core review workflow.
Schedule | Week 1: Test planning & strategy finalization. Week 2: Test case design (functional, API, real-time, moderation scenarios). Week 3-4: Environment/tooling setup + web & mobile automation framework build. Week 5-6: Test execution cycle 1 (functional, integration, real-time features). Week 7: Mobile app testing (device matrix) + content moderation testing. Week 8: Performance testing (load/stress/spike/soak) + security testing. Week 9: Regression cycle 2 (post-fix verification) + UAT support. Week 10: Test summary/exit report, go/no-go release readiness review.
Resources | 1 QA Lead, 2-3 Test Engineers, 1-2 Automation Engineers, 1 Mobile QA Engineer, 1 Performance Engineer, 1 Security Tester, 1 Trust & Safety QA, QA/Staging environments, JIRA + Selenium + Appium + Postman + JMeter licenses/access, real-device lab or cloud device grid.
Test Deliverables | Test strategy document, test cases (functional/API/real-time/mobile/moderation), automation scripts & framework, performance test report, security scan report, content moderation test report, defect reports, traceability matrix, test summary/exit report.
Approval Process | Test plan reviewed by QA Lead, Dev Lead, and Trust & Safety Lead -> approved by Product Owner -> exit report reviewed at go/no-go meeting -> final sign-off by Product Owner and QA Lead.

## Risk Assessment
RISK ASSESSMENT
Risk | Likelihood | Impact | Severity | Mitigation | Owner
Real-time feature (chat/notifications) instability under concurrent load | High | High | Critical | Load-test WebSocket/push infrastructure early and independently of UI testing | Performance Engineer
Content moderation fails to catch policy-violating edge cases | Medium | Critical | Critical | Build a comprehensive policy-violation test data set reviewed with Trust & Safety team | Trust & Safety QA
Mobile OS/device fragmentation causes untested crashes | High | High | High | Define a prioritized device/OS matrix based on real user analytics; use cloud device labs | Mobile QA Engineer
Viral/spike traffic causes outages not caught in standard load tests | Medium | Critical | High | Include spike testing scenarios simulating sudden follower/post surges | Performance Engineer
User data privacy/security gaps (profile data, DMs) exposed via API | Low | Critical | High | Run authenticated API security scans; verify access control on private profiles/messages | Security Tester
Feed ranking/algorithm changes break functional assumptions mid-sprint | High | Medium | High | Maintain traceability matrix; sync with backend team on ranking-service contract changes | QA Lead
Test environment lacks realistic data volume (posts/users/connections) | Medium | High | High | Use synthetic data generation to simulate production-scale social graphs | Automation Engineer
Automation script flakiness on real-time/async UI updates | Medium | Medium | Medium | Use explicit waits/polling for async elements; isolate flaky tests and review weekly | Automation Engineer
App store review delays block mobile release testing timeline | Medium | Medium | Medium | Use TestFlight/Play Internal Testing for early builds; plan buffer before submission | Mobile QA Engineer
Tight release timeline compresses test execution window | High | High | Critical | Prioritize test cases by risk; parallelize manual/automated execution; negotiate scope if needed | QA Lead / PM

## Task Breakdown
TASK BREAKDOWN & MILESTONES
Task | Owner/Team | Start Week | End Week | Status | Deliverable / Milestone
Finalize test strategy & test plan | QA Lead | Week 1 | Week 1 | Not Started | Test Strategy Document
Design functional test cases (registration, profile, posts) | Test Engineers | Week 2 | Week 2 | Not Started | Test Case Repository
Design real-time feature test scenarios (feed, chat, notifications) | Test Engineers | Week 2 | Week 2 | Not Started | Real-Time Scenario Docs
Design API test cases | Automation Engineers | Week 2 | Week 2 | Not Started | API Test Suite (Postman)
Design content moderation test scenarios | Trust & Safety QA | Week 2 | Week 3 | Not Started | Moderation Test Data Set
Set up JIRA project & workflows | QA Lead | Week 1 | Week 1 | Not Started | JIRA Board Configured
Set up test environments (QA/Staging) | DevOps | Week 3 | Week 3 | Not Started | Environment Ready
Prepare test data (seeded users, posts, social graphs) | Test Engineers | Week 3 | Week 3 | Not Started | Test Data Sets
Set up GitHub repo & branching strategy | Automation Engineers | Week 3 | Week 3 | Not Started | GitHub Repository
Build web automation framework (Selenium/Playwright) | Automation Engineers | Week 3 | Week 4 | Not Started | Web Automation Framework
Build mobile automation framework (Appium) | Mobile QA Engineer | Week 4 | Week 5 | Not Started | Mobile Automation Framework
Automate smoke & regression suite | Automation Engineers | Week 4 | Week 6 | Not Started | Automated Regression Suite
Execute functional/integration testing — Cycle 1 | Test Engineers | Week 5 | Week 6 | Not Started | Execution Report Cycle 1
Execute real-time feature testing (feed, chat, notifications) | Test Engineers | Week 6 | Week 6 | Not Started | Real-Time Test Report
Execute mobile app testing (device matrix) | Mobile QA Engineer | Week 7 | Week 7 | Not Started | Mobile Test Report
Execute content moderation testing | Trust & Safety QA | Week 7 | Week 7 | Not Started | Moderation Test Report
Set up & execute JMeter/k6 performance tests | Performance Engineer | Week 8 | Week 8 | Not Started | Performance Test Report
Conduct security scan (OWASP ZAP / Burp Suite) | Security Tester | Week 8 | Week 8 | Not Started | Security Test Report
Regression cycle 2 (post-fix verification) | Test Engineers | Week 9 | Week 9 | Not Started | Execution Report Cycle 2
Defect triage & retest | QA Lead / Dev Team | Week 9 | Week 9 | Not Started | Defect Status Report
UAT support | QA Lead / BA | Week 9 | Week 9 | Not Started | UAT Sign-off
Prepare test summary / exit report | QA Lead | Week 10 | Week 10 | Not Started | Test Summary Report
Go/No-Go release readiness review | QA Lead / PM / PO | Week 10 | Week 10 | Not Started | Sign-off Document

## Deliverables
PROJECT DELIVERABLES
Deliverable | Description | Owner
Project Charter | High-level document defining purpose, objectives, stakeholders, and scope | QA Lead
Test Strategy Document | Overall approach, tools, roles, entry/exit criteria, risk handling | QA Lead
Test Plan | Detailed scope, schedule, resources, deliverables, and approval process | QA Lead
Risk Assessment | Documented risks with likelihood, impact, and mitigation plans | QA Lead
Environment Setup | Configured QA/Staging environments, test data, and mobile build access ready | DevOps
Task Assignments | Ownership matrix — who does what, by when (see Task Breakdown sheet) | QA Lead
GitHub Repository | Central repo for automation code, test scripts, and CI configuration | Automation Engineers
README / Project Overview | Onboarding doc — summary, setup instructions, how to run tests, folder structure | Automation Engineers
Automated Test Suite | Web (Selenium/Playwright) + Mobile (Appium) + API (Postman) regression suites | Automation/Mobile Engineers
Real-Time Feature Test Report | Results of feed, chat, and notification latency/reliability testing | Test Engineers
Mobile App Test Report | iOS/Android functional and device-matrix compatibility results | Mobile QA Engineer
Performance Test Report | Load/stress/spike/soak results against defined thresholds | Performance Engineer
Security Test Report | OWASP ZAP / Burp Suite scan results and remediation status | Security Tester
Content Moderation Test Report | Results of auto-filter, reporting, and moderator workflow verification | Trust & Safety QA
Defect Reports (JIRA) | All logged bugs with severity, status, and resolution history | Test Engineers
Test Summary / Exit Report | Final coverage, pass/fail metrics, open risks, release recommendation | QA Lead

## Defect Log Template
DEFECT / BUG TRACKING TEMPLATE (JIRA-STYLE)
Bug ID | Summary | Module | Severity | Priority | Status | Steps to Reproduce | Reported By | Assigned To
BUG-001 | Push notification not received for new DM when app is backgrounded (Android 14) | Real-Time / Mobile | High | P1 | Open | 1) User A sends DM to User B 2) User B app is backgrounded 3) No push notification appears | [QA Name] | [Dev Name]
Legend:
This is a template — one example row shown. Add real defects below following the same columns; sync with the live JIRA board.