## README
Exploratory Testing & Test Planning — Worked Example
Case: Flipkart — Search, Cart, Exchange Offer & Checkout flow
How this workbook maps to the learning objectives
| Learning objective | Where to look
| Test Charters | Sheet: Test Charters — SBTM missions for search/filter, cart, exchange offer and checkout on the Flipkart app, ready to run as 90-min sessions.
| Exploratory Session Notes | Sheet: Session Notes — A completed 2-hour exploratory session log (tours, personas, bugs, questions, risks).
| Test Plan | Sheet: Test Plan — A full test plan — objectives, scope, strategy, entry/exit criteria, schedule, deliverables.
| Test Strategy | Sheet: Test Strategy — Overall approach, test levels/types, tools, automation strategy, defect management.
| Risk-Based Testing | Sheet: Risk Matrix — Risk identification, scoring (probability x impact) and prioritisation — formula-driven.
Scenario used throughout
Flipkart is a general e-commerce app (electronics, fashion, home & more). The team is releasing an update touching Product Search & Filters, Cart, Exchange Offer (trade-in for mobiles), and Checkout & Payment (COD, UPI, Cards, EMI). This is a realistic, high-traffic, revenue-critical area ahead of Big Billion Days — good for practising exploratory testing, charters, risk-based planning and a full test plan/strategy.

## Test Charters
Session-Based Test Charters (SBTM)
Mission-based charters for 90-minute time-boxed sessions — Flipkart Search, Cart & Checkout
| Charter ID | Mission (Explore ... Using ... To discover ...) | Areas / Features | Resources needed | Risks / Issues to look for | Time-box
| CH-01 | Explore Product Search & Filters using varied search terms (misspellings, model numbers, category filters) to discover irrelevant results or broken filter combinations | Search bar, autosuggest, filter panel (brand/price/rating/exchange available), sort | Test device (Android + iOS), catalog with known SKUs, network throttling tool | Autosuggest showing delisted products, filters not combining correctly (e.g. brand + exchange-available), sort order resetting after filter change | 90 min
| CH-02 | Explore the Cart using multiple product variants (colour/storage) and quantity edge cases to discover pricing or stock-sync issues | Add to cart, Edit variant/qty, Remove item, Save for later, Buy now vs Add to cart | Test accounts, products with limited stock, products under a flash 'Deal of the Day' | Price not updating after a Deal-of-the-Day timer expires, stock oversell (item still shows 'in stock' in cart after selling out), 'Save for later' losing selected variant | 90 min
| CH-03 | Explore the Exchange Offer (trade-in) flow using different old-device conditions and IMEI inputs to discover valuation or eligibility errors | Select exchange > Enter old device details/IMEI > Get valuation > Apply to order | Test accounts, list of eligible/ineligible device models, sample IMEI numbers | Exchange discount applied without valid device confirmation, valuation not updating final payable amount, ineligible device (e.g. damaged) still allowed to proceed | 90 min
| CH-04 | Explore Checkout & Payment (COD, UPI, card, EMI) as a first-time app user (persona) on a slow network to discover confusing steps or payment-state issues | Address selection/add, Payment method selection, EMI plan selection, Order confirmation, Order failure/retry | Persona notes, throttled network, test UPI handle, test card, screen recorder | Unclear pending-payment state, duplicate order created on retry after timeout, EMI tenure/interest not matching what was shown before payment | 60 min
| CH-05 | Explore order placement under interrupted conditions (app backgrounded, network dropped mid-payment) to discover duplicate charges or lost orders | Payment submission, Order confirmation, Order history/tracking | Two devices/network toggle, transaction log or order-history access | Payment debited but order not created, duplicate order on app relaunch, order status stuck on 'Confirming' indefinitely | 60 min
Charter techniques used (for reference)
| Technique | How it's applied above
| Feature tour | CH-01, CH-02 — walk each feature end to end across variants (filters, storage/colour, quantities).
| Complexity tour | CH-03, CH-05 — target trickiest logic: exchange valuation, interrupted payment state.
| Persona | CH-04 — think like a nervous first-time shopper on a weak connection, not a QA engineer.
| Attack pattern | CH-03, CH-05 — invalid IMEIs, ineligible devices, dropped connections, payment retries.
| Heuristic (SFDIPOT) | Structure, Function, Data, Interface, Platform, Operations, Time — used to design CH-01 through CH-05 so all angles are covered.

## Session Notes
Exploratory Session Notes (SBTM Debrief)
Completed 2-hour session covering CH-02 and CH-03 — Flipkart Cart & Exchange Offer
| Session ID | SESS-2026-09-23-01
| Charters covered | CH-02, CH-03
| Tester | Ankita
| Date | 2026-09-22
| Duration | 2 hours (2 x 60-min sub-sessions)
| Environment | Staging (Android app v14.2), iOS Safari web, 3 test accounts, Big Billion Days catalog
Session breakdown
| Time | Activity (setup / test design / execution / bug investigation) | % of session
| 0:00–0:10 | Setup: prepared test accounts, added Deal-of-the-Day items to cart, listed eligible/ineligible exchange devices |  |  | 8%
| 0:10–0:50 | Test design + execution: CH-02 cart edge cases (variant/qty changes, deal-timer expiry) |  |  | 33%
| 0:50–1:05 | Bug investigation: stale deal price issue (see BUG-301) |  |  | 13%
| 1:05–1:50 | Test design + execution: CH-03 exchange valuation and eligibility checks |  |  | 37%
| 1:50–2:00 | Notes clean-up and debrief prep |  |  | 9%
Bugs found
| Bug ID | Description |  | Steps / Where found | Severity
| BUG-301 | Cart still shows the 'Deal of the Day' discounted price after the deal timer has expired, until the app is force-refreshed |  | Add deal item to cart > wait for deal countdown to hit 0 > proceed to cart (Android app) | High
| BUG-302 | Exchange discount is applied to the order total before the old device's IMEI/condition is actually confirmed by the pickup agent step |  | Select exchange > enter IMEI > skip condition confirmation > proceed to payment (iOS Safari web) | Critical
| BUG-303 | Removing an exchange offer after applying it does not restore full item price on the order summary tile |  | Cart with exchange applied > tap 'Remove exchange' (Android app) | Medium
| BUG-304 | 'Save for later' loses the selected storage/colour variant, reverting to the default variant when moved back to cart |  | Cart > Save item for later > Move to cart again | Low
Areas covered / not covered
| Covered | Cart edit/remove/save-for-later on Android; exchange-offer valuation and eligibility on iOS Safari web; deal-timer price sync between cart and catalog
| Not covered | Checkout/payment/EMI (planned CH-04 session), Flipkart Plus coins redemption, gift wrap add-on, Super Coins on Flipkart Axis card
Questions raised / Risk areas identified
| Open questions | Should the exchange discount be provisional until pickup-agent confirmation, and clearly labelled as such to the customer? Confirm with Product. Should cart auto-refresh when a deal timer expires, rather than requiring a manual refresh?
| Risk areas flagged | Exchange valuation being applied before physical device confirmation (BUG-302) is a financial-risk gap — needs a focused session with backend/API testing before Big Billion Days launch

## Test Plan
Test Plan
Flipkart — Search, Cart, Exchange Offer & Checkout Release 14.2
1. Introduction & Objectives
| Purpose | Verify that Product Search & Filters, Cart, Exchange Offer, and Checkout & Payment work correctly, accurately (pricing/valuation) and reliably for Release 14.2, ahead of the Big Billion Days traffic spike.
| Objectives | 1) Confirm functional correctness of search, filter, cart and checkout flows. 2) Confirm pricing and exchange-valuation calculations are always correct, including edge cases. 3) Confirm usability across Android/iOS/web. 4) Surface high-risk defects early via exploratory testing, alongside scripted regression.
2. Scope
| In scope | Search & autosuggest, filters & sort, Cart (add/edit/remove/save-for-later), Exchange Offer (valuation, eligibility, IMEI check), address selection, payment (COD, UPI, card, EMI), order confirmation, order tracking (status only).
| Out of scope | Seller/marketplace dashboard, returns & refunds processing (separate test plan), Flipkart Plus/Super Coins loyalty program, gift cards, customer support chat.
3. Test Strategy (summary)
| Approach | Risk-based combination of scripted functional/regression testing (critical revenue paths, see Test Strategy sheet) and session-based exploratory testing (charters, see Test Charters sheet) for usability, edge cases and pricing/exchange-valuation gaps.
4. Resources & Schedule
| Team | 1 Test Lead, 3 Manual/Exploratory Testers (Android/iOS/Web), 1 Automation Engineer (shared), 1 Backend/API tester (part-time, pricing & exchange-valuation service).
| Schedule | Test design: Days 1-2. Scripted execution: Days 3-5. Exploratory sessions: Days 3-6 (2 sessions/day). Regression + retest: Days 6-7. Sign-off: Day 8, ahead of Big Billion Days go-live.
5. Entry Criteria
| Entry | Build deployed to staging and smoke-tested; test catalog with deal + full-price SKUs provisioned; exchange-eligible/ineligible device list seeded; test cases and charters reviewed; no P1/Blocker defects open from prior build.
6. Exit Criteria
| Exit | 100% of planned scripted test cases executed; 0 open Critical/High defects; all exploratory charters for in-scope areas completed with debrief notes; Medium/Low defects triaged and either fixed or accepted by Product Owner.
7. Deliverables
| Deliverables | Test plan (this document), test charters and session notes, executed test cases, defect reports, risk matrix, test summary report, sign-off email.
8. Risks & Mitigation
| Risks | See 'Risk Matrix' sheet for the full risk register with probability, impact and mitigation per risk (e.g. exchange valuation applied pre-confirmation, deal-timer price sync, duplicate order on payment retry).

## Test Strategy
Test Strategy Document
Flipkart — Search, Cart, Exchange Offer & Checkout Release 14.2
Overall Testing Approach
| Approach | Blend scripted testing for known, high-value, repeatable paths (pricing calculations, exchange valuation, payment flows, order creation) with session-based exploratory testing for discovery of unknown issues, usability problems and stock/deal-timer edge cases — see 'When to use exploratory' below.
Test Levels
| Unit | Developers — covers discount/exchange-valuation calculation logic, filter/sort logic (automated, CI).
| Integration | Automation Engineer — API contracts between Catalog, Cart, Exchange-valuation and Payment services.
| System | QA team — end-to-end scripted + exploratory, as in this workbook.
| UAT | Business/Category stakeholders — sign off against real Big Billion Days shopping scenarios.
Types of Testing
| Functional | Search/filter, cart, exchange offer, checkout, payment — scripted test cases against requirements.
| Exploratory | Charter-driven sessions (see Test Charters sheet) for usability, edge cases, pricing/valuation gaps.
| Security | Payment data handling, exchange-offer abuse (fake IMEI/condition), address/PII protection.
| Compatibility | Android app, iOS app, mobile web (Safari/Chrome); low-end devices and slow networks.
| Performance | Search/filter response time and checkout throughput under Big-Billion-Days-level concurrent load (non-functional, separate NFR plan).
When to Use Exploratory (vs Scripted)
| Guidance | Use exploratory testing for new/changed features (first pass), ambiguous pricing/exchange-valuation rules, usability judgement, and hunting for edge cases scripted tests won't anticipate (e.g. deal timer expiring mid-session). Use scripted testing for regression, revenue-critical calculations, and anything needing repeatable, auditable evidence. The two complement each other — exploratory findings become new scripted regression cases (e.g. BUG-302 becomes a permanent 'exchange discount pending confirmation' test case).
Tools & Techniques
| Tools | Test management: session charter sheet (this workbook) / SBTM notes. Defect tracking: Jira. Automation: Appium (mobile) + Playwright (web) for regression suite. Devices: BrowserStack App Live / Device Farm for cross-device coverage.
| Techniques | Tours (feature, complexity), Personas (first-time shopper, bargain hunter, upgrade-via-exchange buyer), Attack patterns (invalid IMEI, expired deal timers, interrupted payment), Heuristics (SFDIPOT), Risk-based prioritisation (see Risk Matrix).
Automation Strategy
| Strategy | Automate stable, high-value regression paths after they've been validated manually/exploratorily at least once (e.g. standard search, standard checkout with COD/UPI/EMI). Do not automate exploratory sessions — their value is human judgement and adaptability. New exploratory bugs get added to the automated suite once fixed, to prevent regression before the next sale event.
Defect Management
| Process | Log in Jira with: steps to reproduce, environment (device/OS/app version), severity, evidence (screenshot/recording), linked charter/test case ID. Triage daily during active test cycle, twice daily in Big Billion Days crunch week. Severity: Critical = payment/order-creation failure, incorrect financial calculation, or security issue; High = feature broken, no workaround; Medium = feature impaired, workaround exists; Low = cosmetic.

## Risk Matrix
Risk-Based Testing — Risk Matrix
Probability x Impact = Risk Score. Score >=15 = High priority, 8-14 = Medium, <8 = Low
| Risk ID | Risk description | Area | Probability (1-5) | Impact (1-5) | Risk score | Priority | Mitigation / Test focus
| R-01 | Exchange-offer discount applied to order total before the old device's condition/IMEI is actually confirmed | Exchange Offer | 3 | 5 | 15 | High | Dedicated exchange-valuation exploratory session (CH-03); add server-side confirmation-gating regression tests
| R-02 | Cart shows stale 'Deal of the Day' price after the deal timer expires, allowing checkout at the wrong price | Cart/Pricing | 4 | 4 | 16 | High | Boundary-value exploratory session (CH-02); automate a deal-timer price-sync regression check
| R-03 | Payment debited but order not created due to a dropped connection or app backgrounding mid-payment | Checkout/Payment | 2 | 5 | 10 | Medium | Network-interruption exploratory session (CH-05); idempotency check in payment/order API integration tests
| R-04 | Duplicate order created when user retries payment after a timeout | Checkout/Payment | 2 | 5 | 10 | Medium | Covered via CH-04/CH-05; add idempotency-key regression test at API level
| R-05 | EMI tenure or interest shown at checkout does not match what's confirmed on the bank's payment page | Checkout/Payment | 3 | 4 | 12 | Medium | Scripted regression across major banks' EMI plans; spot-check in CH-04 exploratory session
| R-06 | Search/filter combinations return incorrect or irrelevant results (e.g. brand + exchange-available filter) | Search/Filters | 3 | 3 | 9 | Medium | Cross-filter exploratory pass (CH-01); scripted regression matrix for common filter combinations
| R-07 | 'Save for later' loses selected storage/colour variant | Cart/Wishlist | 3 | 2 | 6 | Low | Scripted regression cases for variant persistence; covered incidentally in CH-02 debrief (BUG-304)
| R-08 | Staging environment or catalog data instability delays test execution ahead of Big Billion Days launch | Environment/Process | 2 | 3 | 6 | Low | Daily environment/catalog health-check before sessions; escalation path to DevOps agreed up front
| Scoring legend | Probability & Impact scored 1 (very low) to 5 (very high). Risk score = Probability x Impact. High priority (>=15) risks get exploratory + scripted coverage; Medium (8-14) get scripted coverage; Low (<8) are monitored and covered opportunistically.