## README
Exploratory Testing & Test Planning — Worked Example
Case: Myntra — Product Search, Cart & Checkout flow
How this workbook maps to the learning objectives
| Learning objective | Where to look
| Test Charters | Sheet: Test Charters — SBTM missions for search/filter, cart, and checkout on the Myntra app, ready to run as 90-min sessions.
| Exploratory Session Notes | Sheet: Session Notes — A completed 2-hour exploratory session log (tours, personas, bugs, questions, risks).
| Test Plan | Sheet: Test Plan — A full test plan — objectives, scope, strategy, entry/exit criteria, schedule, deliverables.
| Test Strategy | Sheet: Test Strategy — Overall approach, test levels/types, tools, automation strategy, defect management.
| Risk-Based Testing | Sheet: Risk Matrix — Risk identification, scoring (probability x impact) and prioritisation — formula-driven.
Scenario used throughout
Myntra is a fashion e-commerce app. The team is releasing an update touching Product Search & Filters, Bag (Cart), Coupons/Offers, and Checkout & Payment (incl. Cash on Delivery and UPI). This is a realistic, high-traffic, revenue-critical area — good for practising exploratory testing, charters, risk-based planning and a full test plan/strategy.

## Test Charters
Session-Based Test Charters (SBTM)
Mission-based charters for 90-minute time-boxed sessions — Myntra Search, Bag & Checkout
| Charter ID | Mission (Explore ... Using ... To discover ...) | Areas / Features | Resources needed | Risks / Issues to look for | Time-box
| CH-01 | Explore Product Search & Filters using varied search terms (misspellings, brand names, size/colour filters) to discover irrelevant results or broken filter combinations | Search bar, autosuggest, filter panel (size/price/brand/discount), sort | Test device (Android + iOS), catalog with known SKUs, network throttling tool | Autosuggest showing out-of-stock items, filters not combining correctly (e.g. size + discount), sort order not persisting after filter change | 90 min
| CH-02 | Explore the Bag (cart) using multiple size/colour variants and quantity edge cases to discover pricing or stock-sync issues | Add to bag, Edit size/qty, Remove item, Save for later, Wishlist-to-bag | Test accounts, products with limited stock, products on flash sale | Price not updating after coupon removal, stock oversell (item goes out of stock mid-session but stays in bag), 'Save for later' losing selected size | 90 min
| CH-03 | Explore Coupons & Offers using stacked/expired/invalid codes and edge-case cart values to discover discount-calculation errors | Apply coupon, Auto-applied offers, Bank offer banners, Cart total recalculation | List of active/expired coupon codes, cart with mixed sale + full-price items | Discount applied on already-discounted items twice, expired coupon still accepted, coupon value exceeding cart total causing negative payable amount | 90 min
| CH-04 | Explore Checkout & Payment (COD, UPI, card) as a first-time app user (persona) on a slow network to discover confusing steps or payment-state issues | Address selection/add, Payment method selection, Order confirmation, Order failure/retry | Persona notes, throttled network, test UPI handle, test card, screen recorder | Unclear pending-payment state, duplicate order created on retry after timeout, address form losing data on back navigation | 60 min
| CH-05 | Explore Order placed under interrupted conditions (app backgrounded, network dropped mid-payment) to discover duplicate charges or lost orders | Payment submission, Order confirmation, Order history/tracking | Two devices/network toggle, transaction log or order-history access | Payment debited but order not created, duplicate order on app relaunch, order status stuck on 'Processing' indefinitely | 60 min
Charter techniques used (for reference)
| Technique | How it's applied above
| Feature tour | CH-01, CH-02 — walk each feature end to end across variants (filters, sizes, quantities).
| Complexity tour | CH-03, CH-05 — target trickiest logic: discount stacking, interrupted payment state.
| Persona | CH-04 — think like a nervous first-time shopper on a weak connection, not a QA engineer.
| Attack pattern | CH-03, CH-05 — invalid/expired codes, cart-total edge cases, dropped connections, retries.
| Heuristic (SFDIPOT) | Structure, Function, Data, Interface, Platform, Operations, Time — used to design CH-01 through CH-05 so all angles are covered.

## Session Notes
Exploratory Session Notes (SBTM Debrief)
Completed 2-hour session covering CH-02 and CH-03 — Myntra Bag & Coupons
| Session ID | SESS-2026-09-22-01
| Charters covered | CH-02, CH-03
| Tester | R. Sharma
| Date | 22-Sep-2026
| Duration | 2 hours (2 x 60-min sub-sessions)
| Environment | Staging (Android app v9.4), iOS Safari web, 3 test accounts, End-of-Season-Sale catalog
Session breakdown
| Time | Activity (setup / test design / execution / bug investigation) | % of session
| 0:00–0:10 | Setup: prepared test accounts, added mixed sale + full-price items, listed active/expired coupons |  |  | 8%
| 0:10–0:50 | Test design + execution: CH-02 bag edge cases (size/qty changes, stock-out mid-session) |  |  | 33%
| 0:50–1:05 | Bug investigation: stock oversell issue (see BUG-201) |  |  | 13%
| 1:05–1:50 | Test design + execution: CH-03 coupon stacking and expired-code checks |  |  | 37%
| 1:50–2:00 | Notes clean-up and debrief prep |  |  | 9%
Bugs found
| Bug ID | Description |  | Steps / Where found | Severity
| BUG-201 | Item stays in bag at old price after it goes out of stock and is later restocked at a higher price |  | Add item to bag > simulate stock-out (backend) > restock at new price > proceed to checkout (Android app) | High
| BUG-202 | An expired coupon code ('EOSS10', expired yesterday) is still accepted and applies the discount |  | Bag > Apply coupon > enter expired code 'EOSS10' > Apply (iOS Safari web) | Critical
| BUG-203 | Removing an auto-applied bank offer does not recalculate the payable total shown on the summary tile |  | Bag with bank offer auto-applied > remove payment method that qualified for offer (Android app) | Medium
| BUG-204 | 'Save for later' loses the selected size, reverting to 'Select size' when moved back to bag |  | Bag > Save item for later > Move to bag again | Low
Areas covered / not covered
| Covered | Bag edit/remove/save-for-later on Android; coupon apply/stack/expired scenarios on iOS Safari web; stock-sync between bag and catalog
| Not covered | Checkout/payment (planned CH-04 session), wishlist-to-bag flow, gift wrap add-on, international/NRI checkout
Questions raised / Risk areas identified
| Open questions | Should an item's price be locked at add-to-bag time or always reflect live catalog price? Confirm pricing rule with Product. Is coupon expiry validated server-side or only in the promo-code metadata cache?
| Risk areas flagged | Coupon expiry check (BUG-202) suggests server-side validation may be relying on a stale cache — needs a focused session with backend/API testing before EOSS goes live

## Test Plan
Test Plan
Myntra — Search, Bag, Coupons & Checkout Release 9.4
1. Introduction & Objectives
| Purpose | Verify that Product Search & Filters, Bag, Coupons/Offers, and Checkout & Payment work correctly, accurately (pricing/discounts) and reliably for Release 9.4, ahead of the End-of-Season-Sale traffic spike.
| Objectives | 1) Confirm functional correctness of search, filter, bag and checkout flows. 2) Confirm pricing/discount calculations are always correct, including edge cases. 3) Confirm usability across Android/iOS/web. 4) Surface high-risk defects early via exploratory testing, alongside scripted regression.
2. Scope
| In scope | Search & autosuggest, filters & sort, Bag (add/edit/remove/save-for-later), coupons & auto-applied offers, address selection, payment (COD, UPI, card, wallet), order confirmation, order tracking (status only).
| Out of scope | Seller/merchant dashboard, returns & refunds processing (separate test plan), international/NRI checkout, gift cards, customer support chat.
3. Test Strategy (summary)
| Approach | Risk-based combination of scripted functional/regression testing (critical revenue paths, see Test Strategy sheet) and session-based exploratory testing (charters, see Test Charters sheet) for usability, edge cases and pricing/stock-sync gaps.
4. Resources & Schedule
| Team | 1 Test Lead, 3 Manual/Exploratory Testers (Android/iOS/Web), 1 Automation Engineer (shared), 1 Backend/API tester (part-time, pricing & coupon service).
| Schedule | Test design: Days 1-2. Scripted execution: Days 3-5. Exploratory sessions: Days 3-6 (2 sessions/day). Regression + retest: Days 6-7. Sign-off: Day 8, ahead of EOSS go-live.
5. Entry Criteria
| Entry | Build deployed to staging and smoke-tested; test catalog with sale + full-price SKUs provisioned; coupon codes (valid/expired) seeded; test cases and charters reviewed; no P1/Blocker defects open from prior build.
6. Exit Criteria
| Exit | 100% of planned scripted test cases executed; 0 open Critical/High defects; all exploratory charters for in-scope areas completed with debrief notes; Medium/Low defects triaged and either fixed or accepted by Product Owner.
7. Deliverables
| Deliverables | Test plan (this document), test charters and session notes, executed test cases, defect reports, risk matrix, test summary report, sign-off email.
8. Risks & Mitigation
| Risks | See 'Risk Matrix' sheet for the full risk register with probability, impact and mitigation per risk (e.g. coupon-expiry bypass, stock/price sync, duplicate order on payment retry).

## Test Strategy
Test Strategy Document
Myntra — Search, Bag, Coupons & Checkout Release 9.4
Overall Testing Approach
| Approach | Blend scripted testing for known, high-value, repeatable paths (pricing calculations, payment flows, order creation) with session-based exploratory testing for discovery of unknown issues, usability problems and stock/price edge cases — see 'When to use exploratory' below.
Test Levels
| Unit | Developers — covers discount-calculation logic, filter/sort logic (automated, CI).
| Integration | Automation Engineer — API contracts between Catalog, Bag, Coupon and Payment services.
| System | QA team — end-to-end scripted + exploratory, as in this workbook.
| UAT | Business/Category stakeholders — sign off against real EOSS shopping scenarios.
Types of Testing
| Functional | Search/filter, bag, coupon, checkout, payment — scripted test cases against requirements.
| Exploratory | Charter-driven sessions (see Test Charters sheet) for usability, edge cases, pricing/stock gaps.
| Security | Payment data handling, coupon abuse (stacking/expired), address/PII protection.
| Compatibility | Android app, iOS app, mobile web (Safari/Chrome); low-end devices and slow networks.
| Performance | Search/filter response time and checkout throughput under EOSS-level concurrent load (non-functional, separate NFR plan).
When to Use Exploratory (vs Scripted)
| Guidance | Use exploratory testing for new/changed features (first pass), ambiguous pricing/discount rules, usability judgement, and hunting for edge cases scripted tests won't anticipate (e.g. stock changing mid-session). Use scripted testing for regression, revenue-critical calculations, and anything needing repeatable, auditable evidence. The two complement each other — exploratory findings become new scripted regression cases (e.g. BUG-202 becomes a permanent expired-coupon test case).
Tools & Techniques
| Tools | Test management: session charter sheet (this workbook) / SBTM notes. Defect tracking: Jira. Automation: Appium (mobile) + Playwright (web) for regression suite. Devices: BrowserStack App Live / Device Farm for cross-device coverage.
| Techniques | Tours (feature, complexity), Personas (first-time shopper, bargain hunter, power user), Attack patterns (expired/stacked coupons, stock-out timing, interrupted payment), Heuristics (SFDIPOT), Risk-based prioritisation (see Risk Matrix).
Automation Strategy
| Strategy | Automate stable, high-value regression paths after they've been validated manually/exploratorily at least once (e.g. standard search, standard checkout with COD/UPI). Do not automate exploratory sessions — their value is human judgement and adaptability. New exploratory bugs get added to the automated suite once fixed, to prevent regression before the next sale event.
Defect Management
| Process | Log in Jira with: steps to reproduce, environment (device/OS/app version), severity, evidence (screenshot/recording), linked charter/test case ID. Triage daily during active test cycle, twice daily in EOSS crunch week. Severity: Critical = payment/order-creation failure or security issue; High = feature broken, no workaround; Medium = feature impaired, workaround exists; Low = cosmetic.

## Risk Matrix
Risk-Based Testing — Risk Matrix
Probability x Impact = Risk Score. Score >=15 = High priority, 8-14 = Medium, <8 = Low
| Risk ID | Risk description | Area | Probability (1-5) | Impact (1-5) | Risk score | Priority | Mitigation / Test focus
| R-01 | Expired or invalid coupon codes are still accepted, causing revenue loss at scale during sale events | Coupons/Offers | 3 | 5 | 15 | High | Dedicated coupon exploratory session (CH-03); add server-side expiry validation regression tests
| R-02 | Item price/stock shown in bag does not match live catalog after a flash-sale price change | Bag/Pricing | 4 | 4 | 16 | High | Boundary-value exploratory session (CH-02); automate a price/stock-sync regression check
| R-03 | Payment debited but order not created due to a dropped connection or app backgrounding mid-payment | Checkout/Payment | 2 | 5 | 10 | Medium | Network-interruption exploratory session (CH-05); idempotency check in payment/order API integration tests
| R-04 | Duplicate order created when user retries payment after a timeout | Checkout/Payment | 2 | 5 | 10 | Medium | Covered via CH-04/CH-05; add idempotency-key regression test at API level
| R-05 | Search/filter combinations return incorrect or irrelevant results (e.g. size + discount filter) | Search/Filters | 3 | 3 | 9 | Medium | Cross-filter exploratory pass (CH-01); scripted regression matrix for common filter combinations
| R-06 | Confusing checkout copy or unclear pending-payment state leads first-time users to abandon or retry unnecessarily | Usability/Checkout | 3 | 3 | 9 | Medium | Persona-based session (CH-04); usability review with Product/UX
| R-07 | 'Save for later' or wishlist actions lose selected size/colour variant | Bag/Wishlist | 3 | 2 | 6 | Low | Scripted regression cases for variant persistence; covered incidentally in CH-02 debrief (BUG-204)
| R-08 | Staging environment or catalog data instability delays test execution ahead of EOSS launch | Environment/Process | 2 | 3 | 6 | Low | Daily environment/catalog health-check before sessions; escalation path to DevOps agreed up front
| Scoring legend | Probability & Impact scored 1 (very low) to 5 (very high). Risk score = Probability x Impact. High priority (>=15) risks get exploratory + scripted coverage; Medium (8-14) get scripted coverage; Low (<8) are monitored and covered opportunistically.